## Sheet1
Project Title
|  |  | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34
Activities | Start Date | End Date | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S

## Sheet2
Project Title
| Activities | Start Date | End Date | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34
1 | Project Intro and Proposal Report
1.1 | Research Into Project | 2019-09-23 | 2019-09-25
1.2 | Come up with new Idea | 2019-09-25 | 2019-10-08
1.3 | Project Proposal writing | 2019-10-08 | 2019-10-24
1.4 | Projet Proposal Submition | 2019-10-24
1.5
2 | Component and Understanding
2.1 | Investigate and order required components

## Sheet4
Children Monitoring System
| Activities | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33
1 | Project Intro and Proposal Report | Week 18: EXAM WEEK
1.1 | Research Into Project | bar: Week 3
1.2 | Come up with new Idea | bar: Week 3 to Week 5
1.3 | Project Proposal writing | bar: Week 5 to Week 7
1.4 | Project Proposal Submission | bar: Week 7
2 | Components and Understanding
2.1 | Investigate and order required components | bar: Week 6 to Week 7
2.2 | Begin to learning how to make an Android App | bar: Week 7
2.3 | Milestone 1: Make a practice app | bar: Week 8 to Week 10
2.4 | Understand how sensors is coded in Arduino IDE | bar: Week 8 to Week 11
2.5 | Make the child monitoring device | bar: Week 10 to Week 13
2.6 | Writing the code for monitoring device | bar: Week 11 to Week 15
2.7 | Milestone 2: Send the collected to the cloud through Wi-Fi | bar: Week 14 to Week 16
3 | Manufacturing and Learning
3.1 | Make a solid works model of the Lamp | bar: Week 16
3.2 | Send the model for 3D printing | bar: Week 17
3.3 | Make the Lamp circuit | bar: Week 20 to Week 22
3.4 | Prepare the code for the lamp circuit | bar: Week 21 to Week 24
3.5 | Milestone 3: Receive the data on the lamp circuit through Wi-Fi | bar: Week 23 to Week 25
3.6 | Milestorn 4: Code Android application to receive data through Wi-Fi | bar: Week 8 to Week 17; Week 20 to Week 25
4 | Combination
4.1 | Milestone 5: Run all the parts together simultaneously | bar: Week 25 to Week 26
4.2 | Optional tasks | bar: Week 26
5 | Thesis Writing
5.1 | Start writing a draft thesis
5.2 | Submission of draft thesis | bar: Week 28 to Week 29
5.3 | Final thesis writing | bar: Week 29 to Week 31
5.4 | Submission of final thesis | bar: Week 31 to Week 33

## Sheet5
Children Monitoring System
| Activities | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33
1 | Project Intro and Proposal Report | Week 18: EXAM WEEK
1.1 | Research Into Project | bar: Week 3
1.2 | Come up with new Idea | bar: Week 3 to Week 5
1.3 | Project Proposal writing | bar: Week 5 to Week 7
1.4 | Project Proposal Submission | bar: Week 7
2 | Components and Understanding
2.1 | Investigate and order required components | bar: Week 6 to Week 7
2.2 | Begin to learning how to make an Android App | bar: Week 7
2.3 | Milestone 1: Make a practice app | bar: Week 8 to Week 10
2.4 | Understand how sensors is coded in Arduino IDE | bar: Week 8 to Week 11
2.5 | Make the child monitoring device | bar: Week 10 to Week 13
2.6 | Writing the code for monitoring device | bar: Week 11 to Week 15
2.7 | Milestone 2: Send the collected to the cloud through Wi-Fi | bar: Week 14 to Week 16
3 | Manufacturing and Learning
3.1 | Make a solid works model of the Lamp | bar: Week 16
3.2 | Send the model for 3D printing | bar: Week 17
3.3 | Make the Lamp circuit | bar: Week 20 to Week 22
3.4 | Prepare the code for the lamp circuit | bar: Week 21 to Week 24
3.5 | Milestone 3: Receive the data on the lamp circuit through Wi-Fi | bar: Week 23 to Week 25
3.6 | Milestorn 4: Code Android application to receive data through Wi-Fi | bar: Week 8 to Week 17; Week 20 to Week 25
4 | Combination
4.1 | Milestone 5: Run all the parts together simultaneously | bar: Week 25 to Week 26
4.2 | Optional tasks | bar: Week 26
5 | Thesis Writing
5.1 | Start writing a draft thesis
5.2 | Submission of draft thesis | bar: Week 28 to Week 29
5.3 | Final thesis writing | bar: Week 29 to Week 31
5.4 | Submission of final thesis | bar: Week 31 to Week 33

## Sheet3
Activity\Sensor Reading | Light Sensor | Accelerometer | GPS | Heart Rate Sensor
| Bright | Moving | Moving | Constant
Sleeping | NO | NO | NO | YES
Exercising | YES | YES | YES | NO
Studying | YES | YES | NO | NO